## Sheet1
Date | Work Day | Front end ( Plan ) | Test ( Plan ) | Comment | Back end ( Remarks only ) | Test ( Remarks only )
2017-06-13 | Tuesday | Dropdown scrollbar( third party UI controller ) |  |  | The back end should at least be divided into 2 layers. Use a Model/Controller architecture. 1. At the controller layer, it handles requests sent from the user agent( web browser, mobile browser, or programable HTTP requests ). 2. At the model layer, it mainly works with database. And other data, either static or dynamic, for example, Eg.1 a map between Transaction ID and types, and/or Eg.2 a map between Service order types and sub-types should also be in model layer. Controller layer purpose: 1. Handles requests of normal data queries, eg. transactions, transaction details, transaction status 2. Handle users relevant requests, eg. user' profile. 3. Handle user's status, eg. login/logout, online, login timeout, etc. 4. Handle user agent's status, eg. clear browser cookie, browser cache, browser being closed, etc. 5. Handle user input errors, invalid user input, unsafe data, malicious data, etc. 6. Handle server errors, 404, 500, etc. Controller architecture - multiple layers - life cycle. Layer 1: Authentication and authorisation Layer 2: Validate and sanitise requests Layer 3: Detect headers, decide if data should be pulled from database or use browsers's local data, make redirections, handle cookies, etc Layer 4: Request data from model layer - Model layer should decdide to use a cached version or perform queries to database Layer 5: Add global response headers Layer 6: Add analytical and/or statistical code( if applicable ) Model Layer purpose: 0. Do not use ORM. Ideally, each request from Controller layer should be completed by only one SQL query or one database transaction. 1. Every request must only get/update the data of database from model layer( model module ). 2. Manage database connections, eg. connection pool 3. Manage data cache. 4. Obtain data from database and make it into desired format 5. Use data from controller layer to update the database. Model Layer architecture - TBD | Test should be at least devided into 3 stages 1. UI test 2. Server test 3. Integration test UI test stage target: 0. Ideally, a dummy server should be created for UI test purpose. The dummy server has the capbilities of handling all requests. However dummy server only uses dummy data generated in the code other than from database. The only difference between a dummy server and a real server is in the model layer. The controller layer should be nearly identical. 1. Validate functionality of every UI control works as expected, TexBox, Dropdown, Table, etc. 2. Validate page's layout and pages' routing 3. Cross browser ability Server (Back end ) test target: 0. The server side's test should be performed without UI's intervention. A copy of real database should be setup. Test scripts should be created for regression test purpose. 1. Validate that user's input is sanitised. 2. Validate that appropriate redirection is performed. 3. Validate that error is correctedly generated. 4. Validate that correct data is obtained from database. 5. Validate that database is successfully updated 6. Validate that user is authenticated. 7. Validate that user's session has expired and related action performed. 8. Performance test. Check CPU, memory, database, network, etc. 9. Stress test. Generate random and concurrent requests to the server over the network. Integration test target 0. Based on former UI and server tests. If both were successful, then the integration test is relatively easy. Baisically it tests in a real envirionment, a user can operate at the browser to login, logout, get the data, see the error and update the data, see the result of the update, etc.
2017-06-14 | Wednesday | Table blank page |  | This is a reusable UI control, also used in Transaction Details Page
2017-06-15 | Thursday | Table pagination
2017-06-16 | Friday | Table pagination
2017-06-17 | Saturday
2017-06-18 | Sunday
2017-06-19 | Monday | Table customise
2017-06-20 | Tuesday | Table customise
2017-06-21 | Wednesday | Table customise
2017-06-22 | Thursday | Table sort
2017-06-23 | Friday | Table sort
2017-06-24 | Saturday | Quick search
2017-06-25 | Sunday
2017-06-26 | Monday | Quick Search
2017-06-27 | Tuesday | Quick Search
2017-06-28 | Wednesday | Clear all fields - from UI, data layer, local storage
2017-06-29 | Thursday | Checkbox design of unsolicited response
2017-06-30 | Friday | Loading state of search
2017-07-01 | Saturday | Error message and display
2017-07-02 | Sunday
2017-07-03 | Monday | Error message and display
2017-07-04 | Tuesday | Local error handling
2017-07-05 | Wednesday | Remote error handlling
2017-07-06 | Thursday | User login state
2017-07-07 | Friday | User login/logout options
2017-07-08 | Saturday
2017-07-09 | Sunday
2017-07-10 | Monday | Remote user login/logout simulation
2017-07-11 | Tuesday | MDH logo desgin
2017-07-12 | Wednesday | Page navigation - dashboard/reports/advanced functions
2017-07-13 | Thursday | Page navigation links design
2017-07-14 | Friday | Dropdown calendar box design
2017-07-15 | Saturday
2017-07-16 | Sunday
2017-07-17 | Monday | Dropdown calendar box design
2017-07-18 | Tuesday | Dropdown calendar integration
2017-07-19 | Wednesday | Textbox design with title and value in same box
2017-07-20 | Thursday | Time box design
2017-07-21 | Friday | Time box select options
2017-07-22 | Saturday
2017-07-23 | Sunday
2017-07-24 | Monday | Cascaded dropdown box of service type/subtype/order number
2017-07-25 | Tuesday | Data population in all input boxes - both basic and advanced search
2017-07-26 | Wednesday | Organise/format/validate/sanitize all input values for remote request - both basic and advanced searches
2017-07-27 | Thursday | Dashboard page wrap up - check and finalise
2017-07-28 | Friday | Dashboard page wrap up - check and finalise |  | Due to complexity, 2 days required to verify the style, functions, etc
2017-07-29 | Saturday
2017-07-30 | Sunday
2017-07-31 | Monday | Reports page layout | UI test of Dashboard page may start from here
2017-08-01 | Tuesday | Reports page details - each box's content and buttons
2017-08-02 | Wednesday | Reports page wrap up - check and finalish |  | 1 day only
2017-08-03 | Thursday | Advanced functions page layout | UI test of Reports page may start from here
2017-08-04 | Friday | Create MIRN discovery request box layout
2017-08-05 | Saturday
2017-08-06 | Sunday
2017-08-07 | Monday | Create MIRN discovery request box details, input box, dropdown, buttons
2017-08-08 | Tuesday | Add multiple requests
2017-08-09 | Wednesday | Organise all input data in Create MIRN discovery request
2017-08-10 | Thursday | Add to exclusion list box / NMI Splitting box layout
2017-08-11 | Friday | Add to exclution list box desgin
2017-08-12 | Saturday
2017-08-13 | Sunday
2017-08-14 | Monday | NMI Splitting list design
2017-08-15 | Tuesday | NMI Splitting list scroll bar and local data test
2017-08-16 | Wednesday | Remote data test of NMI Splitting list
2017-08-17 | Thursday | Add to list functionality |  | Not clear as presented. Needs comfirmation from Jinto
2017-08-18 | Friday | Add to list functionality
2017-08-19 | Saturday
2017-08-20 | Sunday
2017-08-21 | Monday | Remove functionality
2017-08-22 | Tuesday | Remove functionality
2017-08-23 | Wednesday | Local data test of add/remove
2017-08-24 | Thursday | Remote data test of add/remove
2017-08-25 | Friday | Local data test of create MIRN discovery request
2017-08-26 | Saturday
2017-08-27 | Sunday
2017-08-28 | Monday | Remote data test of create MIRN discovery request
2017-08-29 | Tuesday | Modal popup UI design
2017-08-30 | Wednesday | Request details |  | Needs comfirmation from Jinto
2017-08-31 | Thursday | Data integration with request details
2017-09-01 | Friday | Advanced functions page - check and wrap up |  | 2 days required
2017-09-02 | Saturday
2017-09-03 | Sunday
2017-09-04 | Monday | Advanced functions page -check and wrap up
2017-09-05 | Tuesday | Details page layout | UI test of Advanced page may start from here
2017-09-06 | Wednesday | Details page utilities - routing from dashboard and back to results functionality
2017-09-07 | Thursday | Master transactions design
2017-09-08 | Friday | Transaction status implementation - status images
2017-09-09 | Saturday
2017-09-10 | Sunday
2017-09-11 | Monday | Associated transactions design
2017-09-12 | Tuesday | Associated transactions with data implementation
2017-09-13 | Wednesday | Local data test in associatiated transactions - Gas and electricity
2017-09-14 | Thursday | Remote data test in associated transactions - Gas and electricity
2017-09-15 | Friday | Details page check and wrap up |  | 1 day
2017-09-16 | Saturday
2017-09-17 | Sunday
2017-09-18 | Monday | Routing functionalities between dashboard reports and advanced functions without page reload | UI test of Details page may start
2017-09-19 | Tuesday | Overall front end development check and finalise |  | 2 days
2017-09-20 | Wednesday | Overall front end development check and finalise
2017-09-21 | Thursday |  | UI test of entire front end development may start
2017-09-22 | Friday
2017-09-23 | Saturday
2017-09-24 | Sunday
2017-09-25 | Monday
2017-09-26 | Tuesday
2017-09-27 | Wednesday
2017-09-28 | Thursday
2017-09-29 | Friday
2017-09-30 | Saturday