## Sheet1
Date | Workday | Front end | Status | Back end ( Anu & Mevan ) | Test
2017-06-13 | Tuesday | Dropdown scrollbar( third party ) |  | API development & unit tests 1. Transaction group and type API 2. Search API 3. Transaction details API 4. Service order type and subtype API 5. Error handling by requests 400, 404, 500
2017-06-14 | Wednesday | Table pagination
2017-06-15 | Thursday | Table pagination
2017-06-16 | Friday | Dropdown calendar box design
2017-06-19 | Monday | Dropdown calendar finalize
2017-06-20 | Tuesday | Textbox design with title and value in same box
2017-06-21 | Wednesday | Table sort
2017-06-22 | Thursday | Table sort
2017-06-23 | Friday | Checkbox design of unsolicited response
2017-06-26 | Monday | Time box design
2017-06-27 | Tuesday | Time box finalize
2017-06-28 | Wednesday | Clear all fields - from UI, data layer, browser's local storage
2017-06-29 | Thursday | Loading state of search design
2017-06-30 | Friday | Search UI integration with search results
2017-07-03 | Monday | Message Box design |  | Objective: Improve APIs based on tests. Tasks: Integration test: 1. Test if we can get the search results from server, after click on the search button. 2. Test if it redirects to the details page, after click on the table result row. Back end test: 1. Work out a test plan on search API that covers as many filters as possible. ( Right now, exclude transaction group, type, service order type and subtype ) 2. Write test cases based on test plan of search API 3. Write test cases for transaction details API. 4. Write test cases for error hanlding. eg.1 When someone makes request other than our API, responds 404 eg.2 When request params are not correct or contains dirty data, responds 400 - bad request eg.3 Anything server can not handle, responds 500
2017-07-04 | Tuesday | Error message and display
2017-07-05 | Wednesday | Organise/format/validate/sanitize all input values for remote request - both basic and advanced searches
2017-07-06 | Thursday | as above
2017-07-07 | Friday | Remote error handlling 404 500 local test
2017-07-10 | Monday | as above
2017-07-11 | Tuesday | Data population in all input boxes - availble in an JS object to make searches.
2017-07-12 | Wednesday | Quick search
2017-07-13 | Thursday | Quick search
2017-07-14 | Friday | Quick search
2017-07-17 | Monday | Page routing - dashboard/reports/advanced functions |  |  | QA( test ) of dashboard page starts here
2017-07-18 | Tuesday | Page navigation icons links design
2017-07-19 | Wednesday | Cascaded dropdown box of service type/subtype integration with my UI control
2017-07-20 | Thursday | MDH logo design
2017-07-21 | Friday | Dashboard page wrap up - check and finalise
2017-07-24 | Monday | Dashboard page wrap up - check and finalise
2017-07-25 | Tuesday | Details page layout
2017-07-26 | Wednesday | Details page utilities - routing from dashboard and back to results functionality
2017-07-27 | Thursday | Master transactions design
2017-07-28 | Friday | Transaction status implementation - status images
2017-07-31 | Monday | Associated transactions design |  | Objective: Assure the integrity of the application. Integration test continued: 1. Test if correct transactions are populated in the transaction results table. 2. Test if in the details page, correct information and status is fetched.
2017-08-01 | Tuesday | Associated transactions with data implementation
2017-08-02 | Wednesday | Local data test in associatiated transactions - Gas and electricity
2017-08-03 | Thursday | Remote data test in associated transactions - Gas and electricity
2017-08-04 | Friday | Details page check and wrap up
2017-08-07 | Monday | Reports page layout |  |  | QA( test ) of details page starts here
2017-08-08 | Tuesday | Reports page details - each box's content and buttons
2017-08-09 | Wednesday | Reports page wrap up - check and finalish
2017-08-10 | Thursday | Routing functionalities between dashboard reports and advanced functions without page reload |  |  | QA( test ) of reports page
2017-08-11 | Friday | Dashboard/Details Page/Reports page front end development check and finalise
2017-08-14 | Monday | Same above |  |  | QA( test ) of routing between pages
2017-08-15 | Tuesday | Pack resource files, minify, concat for deployment
2017-08-16 | Wednesday | Table customise
2017-08-17 | Thursday | Table customise
2017-08-18 | Friday | Table customise
2017-08-21 | Monday | Table blank page
2017-08-22 | Tuesday | Export to csv
2017-08-23 | Wednesday | User login state
2017-08-24 | Thursday | User login/logout options
2017-08-25 | Friday | Remote user login/logout simulation
2017-08-28 | Monday | Advanced functions page layout
2017-08-29 | Tuesday | Create MIRN discovery request box layout
2017-08-30 | Wednesday | Create MIRN discovery request box details, input box, dropdown, buttons
2017-08-31 | Thursday | Add multiple requests
2017-09-01 | Friday | Organise all input data in Create MIRN discovery request
2017-09-04 | Monday | Add to exclusion list box / NMI Splitting box layout
2017-09-05 | Tuesday | Add to exclution list box desgin
2017-09-06 | Wednesday | NMI Splitting list design
2017-09-07 | Thursday | NMI Splitting list scroll bar and local data test
2017-09-08 | Friday | Remote data test of NMI Splitting list
2017-09-11 | Monday | Add to list functionality
2017-09-12 | Tuesday | Remove functionality
2017-09-13 | Wednesday | Local data test of add/remove
2017-09-14 | Thursday | Remote data test of add/remove
2017-09-15 | Friday | Local data test of create MIRN discovery request
2017-09-18 | Monday | Remote data test of create MIRN discovery request
2017-09-19 | Tuesday | Modal popup UI design
2017-09-20 | Wednesday | Request details
2017-09-21 | Thursday | Data integration with request details
2017-09-22 | Friday | Advanced functions page - check and wrap up